## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-1.1 | Collect historical visa status and processing time data from reliable sources | MUST HAVE | Public datasets | Sachin | 3- Completed
Sprint 1 | Sprint 1 | US-1.2 | Remove missing, duplicate, and inconsistent records from visa datasets | MUST HAVE | US-1.1 | Sachin | 3- Completed
Sprint 1 | Sprint 1 | US-1.3 | Preprocess and normalize visa processing time fields | MUST HAVE | US-1.2 | Sachin | 3- Completed
Sprint 1 | Sprint 1 | US-1.4 | Encode categorical attributes such as country, visa type, and status | SHOULD HAVE | US-1.3 | Sachin | 3- Completed
Sprint 1 | Sprint 1 | US-1.5 | Validate cleaned dataset for accuracy and consistency | MUST HAVE | US-1.4 | Sachin | 3- Completed
Sprint 2 | Sprint 2 | US-2.1 | Perform exploratory data analysis to understand distributions and trends | MUST HAVE | Cleaned dataset | Sachin | 3- Completed
Sprint 2 | Sprint 2 | US-2.2 | Analyze approval rate across education levels and experience | MUST HAVE | US-2.1 | Sachin | 3- Completed
Sprint 2 | Sprint 2 | US-2.3 | Create engineered features such as wage_band and education_level | MUST HAVE | US-2.1 | Sachin | 3- Completed
Sprint 3 | Sprint 3 | US_CS_01 | Baseline Modeling: Implementation of Decision Tree and Random Forest classifiers. | MUST HAVE | Data Prep | Sachin | 3- Completed
Sprint 3 | Sprint 3 | US_CS_02 | Hyperparameter Tuning: Execute GridSearchCV and RandomizedSearchCV for model optimization. | MUST HAVE | US_CS_01 | Sachin | 3- Completed
Sprint 3 | Sprint 3 | US_CS_03 | Boosting Algorithms: Train and evaluate AdaBoost and Gradient Boosting models. | SHOULD HAVE | Baseline | Sachin | 3- Completed
Sprint 3 | Sprint 3 | US_CS_04 | Model Evaluation: Generate confusion matrices and finalize the best model for export. | MUST HAVE | Tuning | Sachin | 3- Completed
Sprint 3 | Sprint 3 | US_FE_01 | Data Scrubbing: Handle non-positive employee counts and impute missing values using medians. | MUST HAVE | Raw Data | Sachin | 3- Completed
Sprint 3 | Sprint 3 | US_FE_02 | Wage Normalization: Standardize prevailing wages to an annual format across all units. | MUST HAVE | US_FE_01 | Sachin | 3- Completed
Sprint 3 | Sprint 3 | US_FE_03 | Target Generation: Implement complex logic to derive processing_time_days from visa and date features. | MUST HAVE | Logic Design | Sachin | 3- Completed
Sprint 3 | Sprint 3 | US_FE_04 | Feature Encoding: Execute One-Hot and Binary encoding for categorical variables. | MUST HAVE | US_FE_03 | Sachin | 3- Completed
Sprint 3 | Sprint 3 | US_REG_01 | Regression Baselines: Develop and evaluate Linear Regression and Random Forest models for days prediction. | MUST HAVE | Feature Eng. | Sachin | 3- Completed
Sprint 3 | Sprint 3 | US_REG_02 | Advanced Modeling: Implement HistGradientBoostingRegressor (HGBR) and perform RandomizedSearch tuning. | MUST HAVE | US_REG_01 | Sachin | 3- Completed
Sprint 3 | Sprint 3 | US_REG_03 | Model Comparison: Execute tie-breaking logic based on $R^2$ and RMSE to select the production-ready model. | MUST HAVE | US_REG_02 | Sachin | 3- Completed
Sprint 4 | Sprint 4 | US-4.1 | As a user, I want to submit my visa details through a form to get a prediction. | MUST HAVE | Backend API | Sachin | 3- Completed
Sprint 4 | Sprint 4 | US-4.2 | As a user, I want to toggle between light/dark mode for better accessibility. | SHOULD HAVE | UI Framework | Sachin | 3- Completed
Sprint 4 | Sprint 4 | US-4.3 | As a user, I want to see my prediction history saved in my account. | MUST HAVE | DB Connection | Sachin | 3- Completed
Sprint 4 | Sprint 4 | US-4.4 | As a dev, I want to deploy the app on Render so it is publicly accessible. | MUST HAVE | US-4.1, 4.3 | Sachin | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7