## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Sachin | 2025-12-30 | Missing processing time values in dataset | Sprint 1 | Sachin | Logical | Applied data imputation | 2025-12-31 | Closed | Resolved
2 | Sachin | 2026-01-03 | Inconsistent date formats | Sprint 1 | Sachin | Logical | Standardized date format | 2026-01-04 | Closed | Fixed
3 | Sachin | 2026-01-05 | Invalid categorical values | Sprint 1 | Sachin | Logical | Corrected & encoded values | 2026-01-06 | Closed | Verified
4 | Sachin | 2026-01-10 | Incorrect approval rate due to one-hot encoded education columns | Sprint 2 | Sachin | Logical | Combined columns into single education feature | 2026-01-11 | Closed | Approval rate corrected
5 | Sachin | 2026-01-14 | Wage analysis confusing due to multiple binary wage columns | Sprint 2 | Sachin | Logical | Created unified wage_band feature | 2026-01-15 | Closed | Improved clarity
6 | Sachin | 2026-01-16 | Visualization warning in seaborn plots | Sprint 2 | Sachin | Logical | Modified plot parameters | 2026-01-17 | Closed | clean plots generated
7 | Sachin | 2026-01-18 | Overfitting in baseline Decision Tree (100% training accuracy). | Sprint 3 | Sachin | Logical | Applied pruning via max_depth and min_samples_split. | 2026-01-19 | Closed | Accuracy normalized.
8 | Sachin | 2026-01-19 | Low Recall for 'Denied' class due to imbalanced distribution. | Sprint 3 | Sachin | Logical | Enabled class_weight='balanced' in the parameter grid. | 2026-01-20 | Closed | Recall improved by 12%.
9 | Sachin | 2026-01-20 | Gradient Boosting parameters causing long execution times. | Sprint 3 | Sachin | Maintainability | Optimized RandomizedSearchCV to n_iter=20. | 2026-01-21 | Closed | Training time reduced.
10 | Sachin | 2026-01-22 | Error in company_age calculation due to establishment years in the future. | Sprint 3 | Sachin | Logical | Applied lambda function to cap minimum age at 0. | 2026-01-22 | Closed | Prevents negative age values.
11 | Sachin | 2026-01-23 | Wage normalization failing for records with missing unit_of_wage. | Sprint 3 | Sachin | Standards | Implemented conditional logic to default to annual rate. | 2026-01-23 | Closed | All wages now standardized.
12 | Sachin | 2026-01-24 | Boolean columns from get_dummies causing compatibility issues in CSV export. | Sprint 3 | Sachin | Maintainability | Cast all boolean dummy columns to integer type. | 2026-01-24 | Closed | Ensures 0/1 integer format.
13 | Sachin | 2026-01-24 | Linear Regression showing high MAE (7+ days) due to non-linear feature relationships. | Sprint 3 | Sachin | Logical | Switched to Ensemble methods (RF/HGBR). | 2026-01-25 | Closed | Error reduced significantly.
14 | Sachin | 2026-01-25 | Potential Overfitting detected in Tuned RF ($R^2$ gap between train and test). | Sprint 3 | Sachin | Logical | Generated Learning Curves to visualize variance. | 2026-01-26 | Closed | HGBR proved more stable.
15 | Sachin | 2026-01-26 | Feature Importance ranking inconclusive using standard MDI method. | Sprint 3 | Sachin | Logical | Implemented Permutation Importance on the HGBR model. | 2026-01-27 | Closed | Identified top 5 drivers.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others